## Sheet1
ID | Date | Description | Evaluation | Likelihood | Impact level | Response | Control Measures
1 | 2022-05-03 | Merge conflicts | Loss some potential coding which might break the appliaction |  |  | Save code in a speratepte notepad file before merging code to git | Consitantly push code to git and pull most upto date git file.
2 | 2022-05-03 | Incorrect time estimation | Delay the project by task taking longer than intial estimate |  |  | Adjust user stroies to improve the time estimates
3 | 2022-05-03 | Mockito Knowledge |  |  |  | review the code to see where the errors are present and use online forums to help solve issue. | Review content on QA community and look for addtion guides on the internet
4 | 2022-05-03 | Hardware limitations |  |  |  | Close any unessary programs, or | Keep all unessary programs closed to free up ram space
5 | 2022-05-03 | currupt hardrive | Loss of local files |  |  | pull most recent git and continue | Keep git file upto date by pushing files after each task has been completed
6 | 2022-05-03 | Program fails | Program will fail test as it wont be working |  |  | cross refernece with customer starter class | don’t use code which is unfaminler or not understood
7 | 2022-05-03
8 | 2022-05-03
9 | 2022-05-03
10 | 2022-05-03